## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Rate_Hour | Quantity_People | Total_Costs | PM_Costs | Dev_Team_Costs | Maximum Reduction | Crashing | Crash_Cost_Hour
A | Describe product |  | 18 | 20 | 22 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 1200 | 1200 | 0 | 5 | 1800 | 360
B | Develop marketing strategy |  | 36 | 40 | 44 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 2400 | 2400 | 0 | 10 | 3600 | 360
C | Design brochure | A | 18 | 20 | 22 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 1200 | 1200 | 0 | 5 | 1800 | 360
D | Develop product prototype | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D1 | Requirements analysis | D | 40 | 40 | 40 | 1 | 1 | 1 | 1 | 1 | 60 | 5 | 12000 | 2400 | 9600 | 10 | 3600 | 360
D2 | Software design | D1 | 40 | 40 | 40 | 1 | 1 | 1 | 1 | 1 | 60 | 5 | 12000 | 2400 | 9600 | 10 | 3600 | 360
D3 | System design | D1 | 40 | 40 | 40 | 1 | 0 | 1 | 0 | 1 | 60 | 3 | 7200 | 2400 | 4800 | 10 | 3600 | 360
D4.0 | Begin Code | D2, D3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D4.1 | Coding - Front-end dev | D4.0 | 130 | 150 | 300 | 0 | 1 | 0 | 0 | 0 | 60 | 1 | 9000 | 0 | 9000 | 37.5 | 27000 | 720
D4.2 | Coding - Back-end dev | D4.0 | 160 | 180 | 200 | 0 | 0 | 1 | 0 | 0 | 60 | 1 | 10800 | 0 | 10800 | 45 | 16200 | 360
D4.3 | Coding - Data Scientist | D4.0 | 60 | 80 | 120 | 0 | 0 | 0 | 1 | 0 | 60 | 1 | 4800 | 0 | 4800 | 20 | 10800 | 540
D4.4 | Coding - Data Engineer | D4.0 | 140 | 160 | 180 | 0 | 0 | 0 | 0 | 1 | 60 | 1 | 9600 | 0 | 9600 | 40 | 14400 | 360
D4.5 | End Code | D4.1, D4.2, D4.3, D4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D5 | Write documentation | D4.5 | 18 | 20 | 22 | 1 | 1 | 1 | 1 | 1 | 60 | 5 | 6000 | 1200 | 4800 | 5 | 1800 | 360
D6 | Unit testing | D5 | 30 | 40 | 50 | 0 | 1 | 1 | 0 | 1 | 60 | 3 | 7200 | 0 | 7200 | 10 | 7200 | 720
D7 | System testing | D6 | 30 | 40 | 50 | 1 | 1 | 1 | 0 | 1 | 60 | 4 | 9600 | 2400 | 7200 | 10 | 7200 | 720
D8 | Package deliverables | D5, D7 | 18 | 20 | 22 | 1 | 1 | 1 | 1 | 1 | 60 | 5 | 6000 | 1200 | 4800 | 5 | 2700 | 540
E | Survey potential market | B, C | 28 | 30 | 32 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 1800 | 1800 | 0 | 7.5 | 4050 | 540
F | Develop pricing plan | D8, E | 13 | 15 | 17 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 900 | 900 | 0 | 3.75 | 2025 | 540
G | Develop implementation plan | A, D8 | 28 | 30 | 32 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 1800 | 1800 | 0 | 7.5 | 4050 | 540
H | Write client proposal | F, G | 13 | 15 | 20 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 900 | 900 | 0 | 3.75 | 2025 | 540